## Risk Register
Risk ID | Identification Date | Risk Details |  |  |  |  | Risk Assessment |  |  |  |  | Risk Response |  |  | Revision Date | Risk Status | Comments / Updates
|  | Risk (Event) | Threat / Oppurtunity ? | Cause | Effect | Risk Trigger | Category | Urgency | Probability (.1 to .99) | Impact (1 to 10) | Risk Score (P*I) | Risk Owner | Strategy | Actions
R001 | 2024-04-01 | There is a potential risk of conflict in the project requirements due to differing opinions and expectations from key stakeholders. | Threat | Differing opinions and expectations | delays in the project timeline, increased costs, and potential rework | - Disagreement during requirements meetings. '- Conflicting feedback from stakeholders during requirements validation. | Requirement | High | 0.5 | 6 | 3 | Jone - BA | Mitigation | 1. Facilitate a Requirements Alignment Workshop 2. Establish Clear Communication Channels 3. Document and Prioritize Requirements 4. Conflict Resolution Protocol 5. Regular Updates and Feedback Loops | 2024-07-07 | Open | '- Initial workshop scheduled for 8-July-2024. - Weekly progress meetings established with all stakeholders. - First draft of the documented requirements shared with stakeholders for review and feedback. - Continuous monitoring of stakeholder alignment and addressing any emerging conflicts promptly.
R002 | 2024-05-01 | The extended rainy season may cause significant delays in employees reaching the office due to worsening traffic conditions and flooding. | Threat | Weather Fluctuations | Delay in project timeline and increase in cost | - Weather forecasts indicating extended periods of rain. - Increased traffic congestion and reports of flooding. | Environmental | Moderate | 0.6 | 6 | 3.6 | Dave - PM | Mitigation | - Response Actions - Implement Remote Work Policies - Flexible Working Hours - Transportation Support - Keep employees informed about weather conditions | 2024-07-07 | Open | - Remote work policy in place and communicated to all employees. - Flexible hours policy announced and implemented. - Monitoring weather reports and traffic conditions daily.
R003 | 2024-05-05 | There is a risk of critical IT system failures due to the use of outdated infrastructure. These failures can result in significant downtime, data loss, and disruption of business operations. | Threat | Outdated Infrastructure | Potential financial and reputational damage. | - Increasing frequency of system downtimes and slow performance. - Reports of hardware failures and software compatibility issues. - Feedback from IT staff highlighting the need for infrastructure upgrades | Technical | Moderate | 0.6 | 8 | 4.8 | Jane - IT Manager | Transfer | - Outsource IT Infrastructure Management - Vendor Selection - Contract Negotiation - Regular Monitoring and Reviews | 2024-07-07 | Open | - Initial vendor proposals reviewed and shortlisted. - Contract negotiation in progress, focusing on ensuring robust SLAs. - Transition plan being developed with IT team and vendor.
R004 | 2024-05-06 | The introduction of new AI technology presents an opportunity to significantly improve project efficiency by automating routine tasks, enhancing data analysis, and optimizing resource allocation | Opportunity | New AI technology | Cost Saving with optimizing resource allocation | - Introduction of advanced AI tools in the market. - Positive feedback from early adopters of the technology. - Increased interest in AI capabilities among industry peers. | Innovation | Moderate | 0.7 | 6 | 4.2 | Joy- Architect | Enhance | - Invest in AI Training - Pilot Integration - Optimize Workflows - Continuous Improvement - Monitor Industry Trends | 2024-07-07 | Open | - Training sessions scheduled for next month with a leading AI technology provider. - Pilot project selected for AI tool integration. - Initial workflows identified for optimization. - Regular monitoring of industry trends and updates provided to the team.